## Sheet1
Risk No	Risk	Risk Description	Low	Medium	High
1	Virus	Catching a virus may cause me to take days off to recover	1	0	0
2	Internet Connection	Bad Internet Connection an cause me slow down with my project	1	0	0
3	Ilness	Ilness may cause me to fall behind	0	0	1
4	Laptop damaged	Laptop being damaged mean I can't run my project	0	0	1
5	Lack of knowledge	Knowledge is required everyday to learn something new in the project	0	0	1
6	Variable missing	System variables may cause program not to run	0	1	0
7	Incorrect Database	Connecting the wrong database may cause my application to not run	0	1	0
8	Incorrect Code	Using incorrect code may cause my project to fail	0	0	1

		Risk Handler
	Risk No	Risk response
	1	In case I caught virus I could take few days to recover but in the mean time still improve my skills if I can
	2	Save work after every change so internet connection means nothing
	3	Avoid going out in the cold
	4	Backup everything
	5	Go over lecture notes and training recordings
	6	Add Java and Maven variables into the system
	7	Establish the connection and test it
	8	Test code and run it